## Sheet2
DSI30 Project 4 Tracker
TIMELINE
[6 empty] | DATE | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14 | 2022-08-15
Submission File | Part | To Do | Open Questions | Owner | Due Date | Status | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon
1 | Introduction | Submit for Upload into Google Drive |  | Keziah | 2022-08-13 12:00 | Complete | Discussion, allocation of work
2 | Data Cleaning | 1) Tidy Up for Submission 2) Upload into Google Drive | Done | Edward |  | Complete
2 | EDA | Add more Visualizations for better flow | Pending further addition | Edward | 2022-08-10 12:00 | Complete
3 | Modelling | 1) Optimization 2) Feature Selection/Drop Features + Explain 3) Compile Metrics/Visualisation | Metric | Keziah (Final Compilation) Edward | 2022-08-10 12:00 | Complete
4 | Cost-Benefit Analysis + Conclusion | 1) Research 2) Extra EDA 3) Conclusion |  | Pei Yiing | 2022-08-10 12:00 | Complete
5 | Slides | a) Decide flow of Slides and ownership b) Create Slides c) Convert to PDF (PY) |  | ALL (PY to compile) | 2022-08-14 15:00 | Complete
6 | Project Management Document | 1) Create Document |  | Pei Yiing |  | Complete
7 | Kaggle Submission CSV | 1) Create Columns for Test dataset 2) Run Model to create csv file for Kaggle Submission |  | Keziah Edward | 2022-08-10 12:00 | Complete
8 | README | 1) Write README |  |  |  | Complete
MASTER | Compile for GitHub upload | 1) Compilation of 8 files (4 Notebooks, 1 PDF (Slides), 1 Excel (Gantt Chart), 1 CSV (Kaggle Submission), 1 Markdown (README)) |  | Pei Yiing | 2022-08-14 21:00 | Complete
Submission/Presentation
Scoring Considerations:
1 | We want to reduce False Negative, because the healthcare cost of missing a WNV outbreak is higher than spraying more.
2 | That means, we are increasing Sensitivity = TP/(TP+FN)
3 | Increasing False Positive and therefore REDUCING Specificity = TN/(TN+FP)
4 | and also REDUCING Precision = TP/(TP+FP)
| Model | Performance, Concerns | Features Dropped | Other | Owner | Status
A | Logistic Regression | i) May need to change test size. Ii) Features with high coefficients but unable to explain | Wetbulb, Tmax |  | Pei Yiing | Complete
B | Random Forest | ` |  |  | Keziah | Complete
C | AdaBoost |  | Tmax, Tmin, TAvg (Lag6) |  | Edward | Complete
D | Gradient Boost |  |  |  | Edward | Complete
E | Support Vector Machines |  |  |  | Keziah | Complete
Google Drive Link:
https://drive.google.com/drive/folders/1-bC10NXO8TAVwVMeLJpNAtSfekjN7VnX?usp=sharing